FIXARS LABORATORIES

Strategy & Implementation Plan

UK-based AI Think Tank & Solutions Laboratory

18-Month Roadmap to Series A

March 2026

Confidential - Board & Investor Review

# TABLE OF CONTENTS

- 1. Executive Summary

- 2. Mission & Vision

- 3. Strategic Framework

- 4-7. Phased Implementation (Months 1-18)

- 8. Market Entry Strategy

- 9. Revenue & Go-to-Market

- 10. Technology & Team

- 11. Financial Projections

- 12. Risk & Governance

- 13. Metrics & Partnerships

- 14. Timeline & Appendix

# 1. EXECUTIVE SUMMARY

Fixars Laboratories accelerates from R&D to operational maturity in 18 months with clear revenue generation, geographic expansion, and funding milestones. Strategic differentiation: research + solutions + academy model creates defensible IP and recurring revenue streams.

## Key Metrics

- Revenue: £0 → £180K (M6) → £420K (M12) → £850K+ (M18)

- Team: 4 → 8 → 14 → 25 people

- Funding: Seed £500K-1M (M7) + Series A £2-3M (M17)

- Cash-flow positive: Month 15

# 2. MISSION, VISION & CORE VALUES

## Mission

Deliver world-class AI research, enterprise solutions, and talent development solving Africa's challenges while creating sustainable value.

## Vision

Pan-African AI powerhouse trusted by governments, enterprises, and institutions for competitive advantage and societal impact.

## Core Values

- Excellence: Research rigor and solution quality

- Impact: Real-world economic outcomes

- Accessibility: AI tools available across spectrum

- Integrity: Transparent, ethical practices

- Collaboration: Ecosystem building

- Agility: Rapid market responsiveness

# 3. STRATEGIC FRAMEWORK: 3 PILLARS

## Pillar 1: Applied AI Research & Intelligence

- Research Intelligence Platform: Thesis/publication analysis, patent strategy

- Commodity Intelligence: Real-time price prediction, supply chain optimization

- Sector Intelligence: GovTech, fintech, healthcare, manufacturing

## Pillar 2: Enterprise AI Solutions

- Custom Solutions: ML/AI development (£50-200K per project)

- White-Label Products: Fraud detection, credit scoring, document analysis

- IP Licensing: AfriLLM, research-to-patent monetization

## Pillar 3: AI Talent & Academy

- Certification Programs: AI fundamentals, ML engineering, data science

- Corporate Training: Enterprise upskilling programs

- Talent Pipeline: Direct hire arrangements with partners

# 4. PHASE 1: FOUNDATION (MONTHS 1-3)

## Key Milestones

- M1: UK registration, NITDA alignment, team hiring

- M2: Research Intelligence MVP, GovTech MVP

- M3: Academy MVP (3 courses), equity structure, investor relations

## Financials

- Burn: £8-10K/month | Total: £24-30K | Seed: £40K

# 5. PHASE 2: LAUNCH & TRACTION (MONTHS 4-6)

## Key Milestones

- M4: Public launch, first 2-3 paying customers (£50-75K)

- M5: Academy cohort 1 (30-50 students), GovTech pilot results

- M6: Hire sales team, 5+ enterprise pilots, £70-140K cumulative revenue

## Revenue

- Custom: £45-75K | Research Intelligence: £10-40K | Academy: £15-25K

## Financials

- Burn: £15-18K/month | Cumulative: £70-84K | Pre-seed discussions

# 6. PHASE 3: SCALE (MONTHS 7-12)

## Key Milestones

- M7: Seed funding close (£500K-1M), team expansion (10+ hires)

- M9: UK Public Sector push, Africa expansion (Kenya, South Africa, Ghana)

- M10: AfriLLM Licensing launch (5+ partners)

- M12: £420K+ ARR, Series A prep begins

## Products

- Research Intelligence: 20-30 users | Custom: 8-12 projects | Academy: 3-4 cohorts | GovTech: 2-3 deployments

## Revenue

- Custom: £200-300K | Research: £60-240K | Academy: £60-80K | GovTech: £20-40K | AfriLLM: £25-75K | Total: £365-735K

## Financials

- Burn: £25-35K/month | Total: £150-210K (seed funded) | Runway: 18+ months

# 7. PHASE 4: ACCELERATION (MONTHS 13-18)

## Key Milestones

- M13: Series A fundraising begins (£2-3M)

- M14: UK expansion (10+ deals), M15: Cash-flow positive

- M15: Europe entry (Netherlands, Germany, France)

- M17: Series A close, M18: £850K+ ARR, 20-25 team

## Products

- Research Intelligence SaaS: 50-80 users | Custom: 15-20 projects | GovTech: 5-8 deployments | UK Procurement: 8-12 deals

## Revenue

- Custom: £375-600K | Research SaaS: £120-480K | Academy: £100-150K | GovTech: £80-150K | AfriLLM: £120-400K | Fintech: £100-300K | UK: £240-720K | Total: £735-2.8M cumulative

# 8. MARKET ENTRY STRATEGY

## Priority 1: Nigeria (HIGH EASE)

- Regulatory: NITDA partnership, government AI alignment

- Customers: Education (thesis repository), fintech, government agencies

- Timeline: Pilot to revenue in 2-3 months

- Market: £15B AI contribution by 2030 (27% annual growth)

## Priority 2: Africa - Kenya, South Africa, Ghana (MEDIUM-HIGH)

- Strategy: Leverage Nigeria success, local partnerships

- Revenue: Commodity intelligence, fintech licensing, custom solutions

- Timeline: Enter M10, revenue M12

## Priority 3: UK (MEDIUM)

- Market: £1.17B government AI procurement (55% YoY growth)

- Advantages: SEIS/EIS tax relief, R&D credits, clear regulation

- Timeline: Setup M2-3, revenue M6-9

## Priority 4: Europe (MEDIUM-LOW)

- Markets: Netherlands, Germany, France

- Strategy: Partner-led, white-label licensing

- Timeline: M15+, revenue M16-18

# 9. REVENUE STRATEGY & GO-TO-MARKET

## Revenue Streams

### 1. Custom Solutions (£200-600K by M18)

- Deal size: £25-50K | Cycle: 2-4 months | Margin: 60-70%

### 2. Research Intelligence SaaS (£120-480K by M18)

- Pricing: £200-500/month user | Users: 50-80 by M18 | Margin: 85-90%

### 3. Academy (£100-150K by M18)

- Pricing: £2-5K/student | Cohorts: 5-6 public + 2-3 corporate | Margin: 70-75%

### 4. AfriLLM Licensing (£120-400K by M18)

- Pricing: £5-20K/year per licensee | Partners: 15-20 by M18 | Margin: 90%+

### 5. White-Label Fintech (£100-300K by M18)

- Pricing: £50-150K/year per licensee | Margin: 80-85%

### 6. GovTech (£80-150K by M18)

- Deployments: 5-8 by M18 | Margin: 70-80%

### 7. UK Public Sector (£240-720K by M18)

- Deal size: £30-60K | Contracts: 8-12 by M18 | Margin: 45-55%

## Go-to-Market Channels

- Direct Sales: Enterprise teams targeting Fortune 500 banks, fintech, government

- Partnerships: NITDA, universities, regional tech ecosystems

- Content: Research publications, white papers, thought leadership

- Community: Webinars, events, developer community

# 10. TECHNOLOGY ROADMAP

## Research Intelligence Platform

- M1-2: MVP (thesis analysis, publication scraping)

- M3-6: v1.0 (trend detection, patent analysis, API)

- M7-12: v2.0 (ML insights, commodity pricing, white-label)

- M13-18: SaaS platform (multi-tenant, advanced analytics)

## GovTech Platform

- M2-3: MVP (thesis repository, doc classification)

- M4-6: v1.0 (NLP analysis, government workflows)

- M7-12: v2.0 (compliance automation)

- M13-18: Scale (5+ agencies, customization framework)

## Fintech & Academy Platforms

- Fintech: M3-6 MVP → M7-12 v1.0 → M13-18 v2.0

- Academy: M1-3 MVP → M4-9 v1.0 → M10-18 v2.0 (personalization, labs)

## Infrastructure

- Cloud: AWS Africa + UK for data residency

- Databases: PostgreSQL, MongoDB, Elasticsearch

- ML: MLflow, Kubeflow, SageMaker

- Deployment: Kubernetes, CI/CD pipelines

# 11. TEAM BUILDING & ORGANIZATIONAL DESIGN

## Phase 1 (M1-3): Founding Team (4 people)

- Head of Research | Head of Solutions | Head of Academy | CFO/Ops

## Phase 2 (M4-6): Growth Team (+4-5 people → 8-9 total)

- Sales/BD Lead | 2x Solution Architects | Academy Manager

## Phase 3 (M7-12): Scale Team (+5-6 people → 12-14 total)

- Enterprise Sales Manager | 3-4x Architects | 2x Researchers | ML Engineer

## Phase 4 (M13-18): Expansion Team (+8-11 people → 20-25 total)

- European Sales Lead | 2-3x Account Managers | 2x Researchers | Product Manager

## Organization Structure

- Research Division: Applied AI research, IP, publications

- Solutions Division: Custom projects, white-label, GovTech

- Academy Division: Training, certification, talent pipeline

- Operations: Finance, legal, HR, compliance

# 12. FINANCIAL PLAN & PROJECTIONS

## Burn Rate

- Phase 1 (M1-3): £8-10K/month | Total: £24-30K

- Phase 2 (M4-6): £15-18K/month | Total: £45-54K

- Phase 3 (M7-12): £25-35K/month | Total: £150-210K

- Phase 4 (M13-18): £30-40K/month | Total: £180-240K

## Funding Milestones

- Pre-seed: £40K (bootstrap + angel) → Covers M1-4

- Seed: £500K-1M (M7) → Covers M5-12 + expansion

- Series A: £2-3M (M17) → Geographic expansion, profitability path

## Revenue Projections

- M3: £0 | M6: £70-140K | M9: £200-300K | M12: £365-735K

- M15: £500-1M+ | M18: £735-2.8M cumulative

- M18 run rate: £120-240K/month = £1.4-2.9M annualized

# 13. RISK MITIGATION & GOVERNANCE

## Key Risks

- Market Risk: Low demand → Mitigation: Government pilots, diversified revenue

- Competition Risk: Large firms entry → Mitigation: Defensible IP, first-mover

- Regulatory: Government restrictions → Mitigation: Early engagement, compliant solutions

- Talent: Hiring difficulties → Mitigation: Remote hiring, academy pipeline

- Funding: Series A challenges → Mitigation: Cash-flow positive by M15

## Governance

- Board: Ade (CEO/Chair, 63.45%) + 2-3 independent members

- Advisory Board: 5-7 experts (AI, government, fintech, African markets)

- Meetings: Monthly board, quarterly strategic reviews, weekly leadership team

## Compliance

- Data Privacy: GDPR, CCPA alignment

- AI Ethics: Responsible AI framework, bias testing

- Financial: Monthly P&L, quarterly audits, SEIS/EIS compliance

- Regulatory: NITDA alignment, UK FCA (if fintech), EU AI Act

# 14. KPIs & SUCCESS METRICS

## Phase 1 (M1-3)

- Team: 4 founding hires | Products: 3 MVPs | Partnerships: 2-3 pilots | Brand: 500+ followers

## Phase 2 (M4-6)

- Revenue: £70-140K | Customers: 2-3 paying | Users: 10-15 beta | CAC: £5-10K

## Phase 3 (M7-12)

- Revenue: £365-735K cumulative | Customers: 12-15 active | Team: 12-14 | Unit Econ: 6-8x LTV:CAC

## Phase 4 (M13-18)

- Revenue: £735-2.8M cumulative | Customers: 30-40 active | Team: 18-25 | Cash flow: Positive M15

## Long-term (M24+)

- Revenue: £2-5M ARR | Margin: 30%+ operating | Geographic: 4+ countries | Market position: Top 3 in Africa

# 15. STRATEGIC PARTNERSHIPS & ECOSYSTEM

## Government

- NITDA: Policy alignment, incubation, government referrals

- Nigeria Ministry of Education: Thesis repository pilot

- UK Government Digital Service: Procurement access

## Universities

- University of Lagos: Research collaboration, student pipeline

- UK Universities: Joint research, internship programs

## Corporate

- African banks: Custom solutions, fintech licensing

- Fintech firms: Fraud detection, credit scoring licensing

## Technology

- AWS: Cloud infrastructure, AI services

- Open-source: Model participation, licensing

## Ecosystem

- Webinar series on AI in Africa | Developer community | Research publications

# 16. IMPLEMENTATION TIMELINE

## Quarter 1 (M1-3): Foundation

- W1-2: Registration, NITDA engagement | W3-4: Hiring | W5-8: Product MVPs | W9-12: Academy, partnerships

## Quarter 2 (M4-6): Launch

- W13-16: Public launch, customers | W17-20: Academy cohort, pilots | W21-24: Sales team, enterprise deals

## Quarter 3 (M7-12): Scale

- W25-28: Seed close, team expand | W29-36: UK/Africa entry | W37-44: AfriLLM, Series A prep

## Quarter 4 (M13-18): Acceleration

- W45-48: Series A fundraising | W49-56: UK expansion, Europe entry | W57-64: Series A close, profitability

# 17. APPENDIX: KEY ASSUMPTIONS

## Market Assumptions

- Applied AI services: 25% CAGR through 2030

- Nigeria AI market: 27% annual growth, £15B by 2030

- UK government AI procurement: 55% YoY growth

- Fixars LTV:CAC: 6-8x by M12

## Execution Assumptions

- Team retention: 95%+ (M1-12), 90%+ (M13-18)

- Sales cycle: 2-4 months (enterprise), 3-6 months (government)

- Funding availability: Seed at £10M pre-money, Series A at £15-20M pre-money

## Key Data Sources

- Gartner AI/ML forecasts | NITDA strategy | CCS data | IDC Africa | World Bank