IMPLEMENTATION PLAN

London Content Channels — 12-Month Execution Roadmap

March 2026 • v1.0 • Based on Strategy v4.0

# Phase 1: Launch LondonIn&Out (Weeks 1–8)

Primary objective: Get the first channel live, establish posting rhythm, and begin building audience. LondonIn&Out is the fastest to monetise and the easiest to produce.

## 1.1 Pre-Launch (Week 1)

| # | Task | Owner | Deadline | Priority | Automation Opportunity |
| --- | --- | --- | --- | --- | --- |
| 1.1.1 | Register all social accounts: TikTok, Instagram, YouTube, Facebook Page, X/Twitter | Founder | Day 1–2 | HIGH | Use Namechk to verify handle availability across all platforms simultaneously |
| 1.1.2 | Commission London Fox AI character design (Midjourney or Fiverr brief) | Founder | Day 1–3 | HIGH | Template brief with style references; Midjourney batch generation for variants |
| 1.1.3 | Purchase equipment: gimbal (DJI Osmo SE £79), wireless mic (Rode ME £99) | Founder | Day 1–2 | HIGH | Amazon auto-buy list with affiliate savings |
| 1.1.4 | Set up editing workflow: CapCut templates for IN/OUT split-screen format | Editor | Day 2–5 | HIGH | Create 3–5 reusable CapCut templates for: split-screen, poll overlay, Fox character overlay |
| 1.1.5 | Set up AI voice for London Fox (ElevenLabs account + voice clone) | Founder | Day 3–5 | MEDIUM | ElevenLabs API integration for batch voiceover generation from scripts |
| 1.1.6 | Create content calendar template (4 weeks rolling) | Founder | Day 3–5 | MEDIUM | Notion/Airtable template with cross-platform scheduling; auto-populate recurring formats |
| 1.1.7 | Subscribe to X Premium for LondonIn&Out account (£8/mo) | Founder | Day 1 | LOW | Set up recurring payment |
| 1.1.8 | Set up cross-posting tools (Later, Buffer, or native scheduling) | Founder | Day 4–6 | MEDIUM | Auto-schedule: 1 upload → push to TikTok, IG Reels, YouTube Shorts, Facebook Reels simultaneously |

## 1.2 Content Production & Launch (Weeks 2–8)

| # | Task | Owner | Deadline | Priority | Automation Opportunity |
| --- | --- | --- | --- | --- | --- |
| 1.2.1 | Film first IN/OUT content batch (10–15 videos in one filming day) | Founder | Week 2 | HIGH | Shot list template auto-generated from trending London topics (RSS + Google Trends scraper) |
| 1.2.2 | Edit and publish first 5 TikToks and Instagram Reels | Editor | Week 2 | HIGH | CapCut batch export with pre-set aspect ratios per platform |
| 1.2.3 | Begin daily X/Twitter hot takes and IN/OUT polls | Founder | Week 2 | HIGH | Scheduled tweet queue via TweetDeck/Buffer; poll templates saved |
| 1.2.4 | Post to Facebook Page (repurposed Reels, no watermark) | Editor | Week 2 | MEDIUM | Auto-strip watermarks via SnapTik; batch upload to Facebook native |
| 1.2.5 | Cross-post Shorts to YouTube channel | Editor | Week 2+ | MEDIUM | YouTube Studio bulk upload from exported files |
| 1.2.6 | Establish posting cadence: 5–7 TikToks/week, 4–5 IG Reels, daily X posts | Founder | Week 3+ | HIGH | Content calendar auto-reminders via Notion/Slack notifications |
| 1.2.7 | Monitor analytics weekly: track top-performing formats and topics | Founder | Weekly | MEDIUM | Google Sheets dashboard auto-pulling stats via platform APIs or manual weekly input |
| 1.2.8 | Reach 10K–20K combined followers across platforms | Team | Week 8 | HIGH | Milestone tracker with automated alerts when thresholds crossed |

# Phase 2: Launch LondonGoat + BlackGoat X (Weeks 6–14)

Overlaps with Phase 1 as filming sessions naturally capture content for both channels. Introduces the Goat mascot and begins BlackGoat’s standalone X presence.

## 2.1 Channel Setup

| # | Task | Owner | Deadline | Priority | Automation Opportunity |
| --- | --- | --- | --- | --- | --- |
| 2.1.1 | Register LondonGoat accounts: TikTok, Instagram, YouTube, Facebook | Founder | Week 6 | HIGH | Batch registration using saved details template |
| 2.1.2 | Design Cartoon Goat mascot + Dark Goat variant (Midjourney/Fiverr) | Founder | Week 5–7 | HIGH | Use same Midjourney workflow as Fox; iterate on character sheet |
| 2.1.3 | Set up LondonBlackGoat standalone X/Twitter account | Founder | Week 8 | HIGH | Subscribe to X Premium (£8/mo) |
| 2.1.4 | Create CapCut/AE templates: Goat corner overlay, BlackGoat reaction overlay | Editor | Week 6–8 | HIGH | Reusable After Effects compositions with character position presets |
| 2.1.5 | Begin daily filming capturing LondonGoat street content alongside In&Out | Founder | Week 7+ | HIGH | Single filming day → dual-channel content; shot list template covers both channels |

## 2.2 Content Ramp-Up

| # | Task | Owner | Deadline | Priority | Automation Opportunity |
| --- | --- | --- | --- | --- | --- |
| 2.2.1 | Launch LondonGoat with 7–10 TikToks/week + daily Stories | Editor | Week 8+ | HIGH | Batch editing pipeline: raw clips → auto-trim → Goat overlay → export |
| 2.2.2 | Start BlackGoat series within LondonGoat from week 10 | Founder | Week 10 | MEDIUM | Content tagging system to flag BlackGoat-suitable clips |
| 2.2.3 | Launch BlackGoat X account with 3–6 tweets/day + commentary threads | Founder | Week 8+ | HIGH | Morning news scraper → auto-generate tweet draft templates from headlines (RSS/API) |
| 2.2.4 | Begin “BlackGoat Reads the Papers” TikTok/Reel series (weekly) | Editor | Week 10+ | MEDIUM | Template: headline screenshot + character reaction = 30–60s video |
| 2.2.5 | Cross-platform repurpose: LondonGoat content → Facebook, YouTube Shorts | Editor | Week 8+ | MEDIUM | Auto-export pipeline to all 4 platforms per piece |

# Phase 3: Launch PeoplesofLondon + News Ecosystem (Months 4–6)

The emotional anchor channel goes live, and the cross-channel news content ecosystem activates. One London news story now generates 8–12 pieces across all channels.

| # | Task | Owner | Deadline | Priority | Automation Opportunity |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Register PeoplesofLondon: Instagram (primary), YouTube, Facebook, TikTok | Founder | Month 4 | HIGH | Batch account setup |
| 3.2 | Create Facebook Group “Stories of London” from day one | Founder | Month 4 | MEDIUM | Pre-built group description + rules template |
| 3.3 | Film first 3–5 street interviews / portrait stories | Founder | Month 4 | HIGH | Interview question bank template; consent form template (digital) |
| 3.4 | Produce first mini-documentary for YouTube (3–5 minutes) | Editor | Month 4–5 | HIGH | Mini-doc template: intro → story → reflection → call-to-action |
| 3.5 | Establish 1–2 stories/week publishing cadence | Team | Month 5+ | HIGH | Calendar auto-scheduling for weekly story pipeline |
| 3.6 | Activate cross-channel news ecosystem: 1 story → 4 channel angles | Team | Month 5+ | HIGH | News event → auto-generate content briefs for each channel (template-driven) |
| 3.7 | Ramp BlackGoat X to daily posting with full news commentary | Founder | Month 5 | HIGH | Morning dashboard: top London headlines + draft tweet suggestions |
| 3.8 | Start weekly “Weekly Headlines IN/OUT” round-up Reel for In&Out | Editor | Month 5+ | MEDIUM | Templated round-up format; auto-pull week’s best-performing topics |

# Phase 4: Full Ecosystem + Scale (Months 6–12)

All four channels fully operational across all six platforms. The content machine is humming. Time to scale production, build owned media, and pursue partnerships.

| # | Task | Owner | Deadline | Priority | Automation Opportunity |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Hire freelance video editor to handle volume (£500–£1,500/mo) | Founder | Month 7–8 | HIGH | Task management via Trello/Notion with automated assignment per channel |
| 4.2 | Scale to 3–4 filming days/week generating 30–40 pieces across all channels | Team | Month 7+ | HIGH | Shot list generator: trending topics + calendar events + news → filming schedule |
| 4.3 | Launch LondonIn&Out email newsletter (weekly trend round-up) | Founder | Month 6–7 | HIGH | Beehiiv or Substack; auto-populate from week’s top In&Out content + newsletter template |
| 4.4 | Launch merchandise: character stickers, limited-edition prints | Founder | Month 8–10 | MEDIUM | Print-on-demand (Printful/Gelato) integrated with Shopify; zero inventory risk |
| 4.5 | Approach tourism boards, councils, media outlets for paid partnerships | Founder | Month 8+ | MEDIUM | Media kit template auto-populated with latest stats; outreach email templates |
| 4.6 | Pitch BlackGoat for radio/podcast guest spots | Founder | Month 9+ | LOW | Podcast pitch template; target list of London-focused shows |
| 4.7 | Explore ticketed X Spaces: monthly “Devil’s Advocate Hour” | Founder | Month 9+ | LOW | Recurring calendar event; auto-promote across channels 48h before |
| 4.8 | Register as sole trader with HMRC (when earnings exceed £1,000) | Founder | When applicable | HIGH | Set calendar reminder; use HMRC online self-assessment |
| 4.9 | Set up accounting: track expenses, deductibles, quarterly tax estimates | Founder | Month 4+ | HIGH | FreeAgent or Xero; auto-categorise expenses; receipt scanning via app |

# Automation & Efficiency Playbook

These are the key systems to build that will save the most time and make the multi-channel operation viable for a small team. Think of automation like plumbing — once it’s installed, content flows to all platforms without you carrying buckets to each one.

## Content Distribution Automation

| System | What It Does | Tools | Time Saved |
| --- | --- | --- | --- |
| Cross-Platform Publisher | One video upload → auto-distributes to TikTok, IG Reels, YouTube Shorts, Facebook Reels | Later, Buffer, or Repurpose.io | 2–3 hours/day |
| Watermark Stripper | Auto-removes TikTok watermarks for Facebook/YouTube re-upload | SnapTik API or SaveTik | 30 min/day |
| Aspect Ratio Converter | Auto-converts 9:16 vertical to 1:1 (carousels), 16:9 (YouTube long-form) | FFmpeg script or CapCut batch | 1 hour/day |
| Caption Generator | Auto-generates captions/subtitles for all video content | CapCut auto-captions or Descript | 1–2 hours/day |

## Content Ideation Automation

| System | What It Does | Tools | Time Saved |
| --- | --- | --- | --- |
| London News Scraper | Morning dashboard of top London headlines from Evening Standard, Metro, BBC London, TimeOut | RSS reader (Feedly) + Google Alerts | 1 hour/day |
| Trending Topic Tracker | Monitors TikTok/X trends related to London, culture, food, property, transport | TrendTok, Google Trends alerts, X trending API | 30 min/day |
| Content Brief Generator | One news story → auto-generates 4 content briefs (one per channel angle) | Notion template + AI (ChatGPT/Claude) | 1 hour/day |
| Shot List Builder | Auto-generates weekly filming schedule from trending topics + calendar events | Airtable + Google Calendar integration | 2 hours/week |

## Analytics & Reporting Automation

| System | What It Does | Tools | Time Saved |
| --- | --- | --- | --- |
| Performance Dashboard | Weekly auto-report: views, followers, engagement rate, revenue per platform per channel | Google Sheets + API pulls or Metricool | 3 hours/week |
| Milestone Alerts | Auto-notify when follower/view thresholds hit (10K, 50K, 100K) | Custom script or Metricool alerts | Prevents missed milestones |
| Revenue Tracker | Consolidates earnings across all platforms + brand deals into one view | FreeAgent/Xero + manual brand deal log | 2 hours/week |
| Viral Alert | Flags any post exceeding 5x average views within 24 hours for immediate cross-promotion | Custom notification script | Captures viral moments faster |

# Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| TikTok ban or restrictions in UK | MEDIUM | HIGH | 6-platform diversification; YouTube Shorts as direct substitute; newsletter as owned media backup |
| Algorithm changes reduce organic reach | HIGH | MEDIUM | Multi-platform hedging; email newsletter; Facebook Groups for owned audience |
| Burnout from daily multi-platform posting | HIGH | HIGH | Batch filming (1 day = 1 week content); hire editor Month 7–8; automation stack |
| Defamation risk from BlackGoat commentary | LOW | HIGH | Character framing; fact-check all claims; satirise institutions not individuals; legal review of borderline content |
| Slow audience growth (below conservative) | MEDIUM | MEDIUM | Lean expense structure; focus on In&Out first; iterate formats based on analytics |
| Brand safety concerns limiting monetisation | MEDIUM | MEDIUM | BlackGoat runs as series within LondonGoat on video platforms; standalone only on X |
| Competitor copies the multi-channel concept | LOW | LOW | Execution speed and AI character brand loyalty create moat; first-mover advantage |

This implementation plan is a living document. Review weekly during Phase 1–2, fortnightly during Phase 3–4. Adjust timelines based on actual performance data, not assumptions.