## Master Task Tracker
LONDON CONTENT CHANNELS — Master Launch Tracker
Phase | Task ID | Task Description | Owner | Deadline | Status | Priority | % Complete | Notes / Automation
Phase 1 | 1.1.1 | Register all social accounts for LondonIn&Out (TikTok, IG, YT, FB, X) | Founder | Week 1 | Not Started | HIGH | 0% | Use Namechk for handle availability check
Phase 1 | 1.1.2 | Commission London Fox AI character design | Founder | Week 1 | Not Started | HIGH | 0% | Midjourney batch generation or Fiverr brief template
Phase 1 | 1.1.3 | Purchase equipment (gimbal £79, mic £99) | Founder | Week 1 | Not Started | HIGH | 0% | Amazon auto-buy list
Phase 1 | 1.1.4 | Set up CapCut templates for IN/OUT split-screen format | Editor | Week 1 | Not Started | HIGH | 0% | Create 3-5 reusable templates
Phase 1 | 1.1.5 | Set up ElevenLabs AI voice for London Fox | Founder | Week 1 | Not Started | MEDIUM | 0% | API integration for batch voiceover
Phase 1 | 1.1.6 | Create content calendar (Notion/Airtable) | Founder | Week 1 | Not Started | MEDIUM | 0% | Template with cross-platform scheduling
Phase 1 | 1.1.7 | Subscribe to X Premium for In&Out (£8/mo) | Founder | Week 1 | Not Started | LOW | 0% | Recurring payment setup
Phase 1 | 1.1.8 | Set up cross-posting tools (Later/Buffer/Repurpose.io) | Founder | Week 1 | Not Started | MEDIUM | 0% | 1 upload → auto-push to all platforms
Phase 1 | 1.2.1 | Film first IN/OUT content batch (10-15 videos) | Founder | Week 2 | Not Started | HIGH | 0% | Shot list from trending London topics
Phase 1 | 1.2.2 | Edit and publish first 5 TikToks + IG Reels | Editor | Week 2 | Not Started | HIGH | 0% | CapCut batch export per platform
Phase 1 | 1.2.3 | Begin daily X hot takes and IN/OUT polls | Founder | Week 2 | Not Started | HIGH | 0% | Scheduled tweet queue via Buffer
Phase 1 | 1.2.4 | Repurpose content to Facebook (native, no watermark) | Editor | Week 2 | Not Started | MEDIUM | 0% | Auto-strip watermarks; batch upload
Phase 1 | 1.2.5 | Cross-post Shorts to YouTube | Editor | Week 2 | Not Started | MEDIUM | 0% | YouTube Studio bulk upload
Phase 1 | 1.2.6 | Establish posting cadence: 5-7 TikTok/wk, 4-5 IG, daily X | Founder | Week 3 | Not Started | HIGH | 0% | Auto-reminders via Notion/Slack
Phase 1 | 1.2.7 | Set up weekly analytics monitoring | Founder | Week 3 | Not Started | MEDIUM | 0% | Google Sheets dashboard or Metricool
Phase 1 | 1.2.8 | Hit 10K-20K combined followers | Team | Week 8 | Not Started | HIGH | 0% | Milestone tracker with alerts
Phase 2 | 2.1.1 | Register LondonGoat accounts (TikTok, IG, YT, FB) | Founder | Week 6 | Not Started | HIGH | 0% | Batch registration
Phase 2 | 2.1.2 | Design Cartoon Goat + Dark Goat mascots | Founder | Week 6 | Not Started | HIGH | 0% | Same Midjourney workflow as Fox
Phase 2 | 2.1.3 | Set up LondonBlackGoat standalone X account + Premium | Founder | Week 8 | Not Started | HIGH | 0% | X Premium £8/mo
Phase 2 | 2.1.4 | Create Goat + BlackGoat overlay templates (CapCut/AE) | Editor | Week 7 | Not Started | HIGH | 0% | Reusable AE compositions
Phase 2 | 2.1.5 | Begin dual-channel filming (In&Out + Goat) | Founder | Week 7 | Not Started | HIGH | 0% | Single filming day → dual content
Phase 2 | 2.2.1 | Launch LondonGoat: 7-10 TikToks/wk + daily Stories | Editor | Week 8 | Not Started | HIGH | 0% | Batch editing pipeline
Phase 2 | 2.2.2 | Start BlackGoat series within LondonGoat (Week 10) | Founder | Week 10 | Not Started | MEDIUM | 0% | Content tagging system
Phase 2 | 2.2.3 | Launch BlackGoat X: 3-6 tweets/day + threads | Founder | Week 8 | Not Started | HIGH | 0% | Morning news scraper → draft tweets
Phase 2 | 2.2.4 | Begin 'BlackGoat Reads the Papers' TikTok series | Editor | Week 10 | Not Started | MEDIUM | 0% | Template: headline + character reaction
Phase 2 | 2.2.5 | Cross-platform repurpose: Goat → FB, YT Shorts | Editor | Week 8 | Not Started | MEDIUM | 0% | Auto-export pipeline
Phase 3 | 3.1 | Register PeoplesofLondon (IG, YT, FB, TikTok) | Founder | Month 4 | Not Started | HIGH | 0% | Batch account setup
Phase 3 | 3.2 | Create FB Group 'Stories of London' | Founder | Month 4 | Not Started | MEDIUM | 0% | Pre-built description + rules template
Phase 3 | 3.3 | Film first 3-5 street interviews | Founder | Month 4 | Not Started | HIGH | 0% | Interview question bank + consent form
Phase 3 | 3.4 | Produce first YouTube mini-doc (3-5 min) | Editor | Month 5 | Not Started | HIGH | 0% | Mini-doc template structure
Phase 3 | 3.5 | Establish 1-2 stories/week cadence | Team | Month 5 | Not Started | HIGH | 0% | Calendar auto-scheduling
Phase 3 | 3.6 | Activate cross-channel news ecosystem | Team | Month 5 | Not Started | HIGH | 0% | 1 story → 4 channel briefs (template)
Phase 3 | 3.7 | Ramp BlackGoat X to daily news commentary | Founder | Month 5 | Not Started | HIGH | 0% | Morning headline dashboard
Phase 3 | 3.8 | Start weekly 'Headlines IN/OUT' round-up Reel | Editor | Month 5 | Not Started | MEDIUM | 0% | Templated round-up format
Phase 4 | 4.1 | Hire freelance video editor (£500-£1,500/mo) | Founder | Month 7 | Not Started | HIGH | 0% | Trello/Notion task management
Phase 4 | 4.2 | Scale to 30-40 pieces/week across all channels | Team | Month 7 | Not Started | HIGH | 0% | Shot list generator automation
Phase 4 | 4.3 | Launch email newsletter (Beehiiv/Substack) | Founder | Month 7 | Not Started | HIGH | 0% | Auto-populate from week's top content
Phase 4 | 4.4 | Launch merchandise (stickers, prints) | Founder | Month 9 | Not Started | MEDIUM | 0% | Print-on-demand via Printful/Gelato
Phase 4 | 4.5 | Approach tourism boards/councils for partnerships | Founder | Month 8 | Not Started | MEDIUM | 0% | Media kit template + outreach emails
Phase 4 | 4.6 | Pitch BlackGoat for radio/podcast guest spots | Founder | Month 9 | Not Started | LOW | 0% | Podcast pitch template
Phase 4 | 4.7 | Launch ticketed X Spaces 'Devil's Advocate Hour' | Founder | Month 9 | Not Started | LOW | 0% | Recurring calendar + auto-promote
Phase 4 | 4.8 | Register as sole trader with HMRC | Founder | When needed | Not Started | HIGH | 0% | Calendar reminder at £1K earnings
Phase 4 | 4.9 | Set up accounting (FreeAgent/Xero) | Founder | Month 4 | Not Started | HIGH | 0% | Auto-categorise + receipt scanning

## Dashboard
LAUNCH DASHBOARD — Progress Overview
Metric | Phase 1 | Phase 2 | Phase 3 | Phase 4 | TOTAL
Total Tasks | 16 | 10 | 8 | 9 | 43
Complete | 0 | 0 | 0 | 0 | 0
In Progress | 0 | 0 | 0 | 0 | 0
Not Started | 16 | 10 | 8 | 9 | 43
Blocked | 0 | 0 | 0 | 0 | 0
% Complete | 0% | 0% | 0% | 0% | 0%

## Budget Tracker
BUDGET & EXPENSE TRACKER
Category | Item | Budget (£) | Actual (£) | Variance (£) | Status
Equipment | Camera (smartphone/Sony ZV-1F) | 0 | 0 | 0 | Pending
Equipment | DJI Osmo Mobile SE gimbal | 79 | 0 | 79 | Pending
Equipment | Rode Wireless ME microphone | 99 | 0 | 99 | Pending
Software | CapCut (free) / Adobe Premiere | 0 | 0 | 0 | Pending
Software | Midjourney subscription (£8/mo x 12) | 96 | 0 | 96 | Pending
Software | Canva Pro (£10/mo x 12) | 120 | 0 | 120 | Pending
Software | ElevenLabs AI voice (£5/mo x 12) | 60 | 0 | 60 | Pending
Platform | X Premium x4 accounts (£32/mo x 12) | 384 | 0 | 384 | Pending
AI Characters | Character design (Fox, Goat, Dark Goat) | 300 | 0 | 300 | Pending
Content | Cross-posting tool (Later/Buffer, £15/mo x 10) | 150 | 0 | 150 | Pending
Content | Freelance editor (Month 7-12, £1,000/mo x 6) | 6000 | 0 | 6000 | Pending
Business | HMRC registration / accountant | 200 | 0 | 200 | Pending
Business | FreeAgent/Xero accounting (£12/mo x 12) | 144 | 0 | 144 | Pending
Merch | Print-on-demand setup (Printful/Gelato) | 100 | 0 | 100 | Pending
Marketing | Newsletter platform (Beehiiv free tier) | 0 | 0 | 0 | Pending
| TOTAL | 7732 | 0 | 7732

## Content Calendar
WEEKLY CONTENT CALENDAR TEMPLATE
Day | Channel | Platform | Format | Topic / Hook | Status | Scheduled Time | Performance Notes
Monday | LondonIn&Out | TikTok | IN/OUT Reel (60-90s) |  | Draft
Monday | LondonIn&Out | X/Twitter | Hot Take Tweet + Poll |  | Draft
Monday | LondonGoat | TikTok | Street Scene Reel (15-60s) |  | Draft
Monday | BlackGoat (X) | X/Twitter | News Commentary Tweet |  | Draft
Tuesday | LondonIn&Out | Instagram | IN/OUT Carousel (5 slides) |  | Draft
Tuesday | LondonGoat | TikTok | London Walk Reel |  | Draft
Tuesday | LondonGoat | Instagram Stories | Behind-the-scenes Story |  | Draft
Wednesday | LondonIn&Out | TikTok | IN/OUT Reel |  | Draft
Wednesday | LondonIn&Out | Facebook | IN/OUT Reel (native upload) |  | Draft
Wednesday | BlackGoat | TikTok | BlackGoat Reads Papers Reel |  | Draft
Wednesday | PeoplesofLondon | Instagram | Portrait + Long Caption |  | Draft
Thursday | LondonGoat | TikTok | Street Scene Reel |  | Draft
Thursday | LondonGoat | YouTube Shorts | Street Moment Short |  | Draft
Thursday | BlackGoat (X) | X/Twitter | Devil's Advocate Thread |  | Draft
Friday | LondonIn&Out | TikTok | IN/OUT Reel |  | Draft
Friday | LondonIn&Out | Instagram Carousel | Weekly IN/OUT Round-up |  | Draft
Friday | LondonGoat | TikTok | Hidden Gem Reel |  | Draft
Friday | PeoplesofLondon | YouTube | Mini-Documentary (3-5min) |  | Draft
Saturday | LondonGoat | TikTok | Weekend London Reel |  | Draft
Saturday | LondonIn&Out | X/Twitter Poll | Weekly IN or OUT? Vote |  | Draft
Sunday | PeoplesofLondon | Facebook | Community Story Post |  | Draft
Sunday | BlackGoat (X) | X/Twitter Thread | Weekly News Round-up Thread |  | Draft